| SKSPRP3 Plan and monitor the manufacture of props to meet production needs |  |
| --- | --- |

Overview

​This standard is about identifying the requirements for manufacturing props from script breakdowns in house or outsourced. It is about planning and scheduling the manufacturing requirements and monitoring progress.

This standard may be suitable for the role of Props master. *

*This is a generic term and not gender specific.

Performance criteria

You must be able to:

- ​identify the requirements for props from script breakdowns

- liaise with all other departments, suppliers or manufacturers when required to identify prop requirements for each scene

- justify having props made or manufactured

- analyse information sources to identify manufacturing requirements

- prepare estimates of the materials, tools, and equipment for the manufacture of props

- identify the characteristics of the materials and confirm requirements with decision makers

- schedule the manufacturing of props to make them available when required, allowing sufficient time for contingencies

- obtain materials and make supply arrangements, so that manufacturing can be completed to the agreed deadline

- identify the tasks and skills required to manufacture props, and assign appropriate personnel to manufacturing tasks

- confirm the availability, safety, and security of manufacturing facilities

- monitor and review manufacturing operations to confirm that the number and quality of props meets requirements, and that they are produced to agreed deadlines

- record and file monitoring information, to inform future manufacturing operations

- use monitoring information to provide other decision makers with progress reports

- identify factors affecting quality, output and the overall schedule and put contingencies in place

- comply with health and safety legislation, regulations, and protocols

Knowledge and understanding

You need to know and understand:

- ​methods of identifying requirements for manufacturing props from script breakdowns

- criteria for assessing the need to make props

- the manufacturing requirements and deadlines

- sources of information about manufacturing companies, and their capabilities

- how to prepare estimates of materials, tools, and equipment

- how to keep accurate records and reports of props manufactured

- how to plan for contingencies

- how to determine the skills required to make props

- the required manufacturing facilities, including their safety features

- different manufacturing methods and how to select the most suitable method

- how to deal with factors affecting quality, output, and the schedule

- the relevant health and safety legislation, regulations, and protocols

Developed by

ScreenSkills

Version Number

3

Date Approved

30 Mar 2022

Indicative Review Date

30 Mar 2026

Validity

Current

Status

Original

Originating Organisation

ScreenSkills

Original URN

SKSPRP3

Relevant Occupations

Arts, Media and Publishing, Crafts, Creative Arts and Design, Media and Communication, Media Associate Professionals, Performing Arts

Suite

Props for Productions

Keywords

props; plan props; monitor manufacture of props; script breakdowns; manufacturing requirements; costs; props master;