| COGST3-07 Prepare and manage budgets for scientific or technical workplace activities |  |
| --- | --- |

Overview

This standard covers the competences you need to prepare

and manage budgets for scientific or technical workplace

activities, in accordance with approved procedures and

practices.

You will be required to demonstrate that you can prepare,

submit and agree a budget for a set period. This will involve

monitoring actual performance against the agreed budget.

You will take the necessary action in response to any

identified variances and unforeseen developments in

accordance with workplace procedures.

The activity is likely to be undertaken by someone in a

science related work setting, including individuals working

in hospitals, scientific laboratories, schools and universities.

Performance criteria

You must be able to:

P1 ensure that your work is carried out in accordance with

workplace procedures

P2 use safe practices and the appropriate personal

protection equipment (PPE) where scientific or technical

activities are performed

P3 identify and agree the business and scientific or

technical requirements of your role in the workplace

P4 establish processes that deliver scientific or technical

outcomes based on organisational goals and aims

P5 evaluate available information and consult with others to

prepare budget plans for activities

P6 submit proposed budgets to the relevant people in the

organisation, for approval and to assist the overall planning

process

P7 use the agreed budget plans to start, monitor and

control delivery of scientific or technical activities

P8 evaluate variances between what was planned in the

budget and what actually happened in the workplace

P9 take prompt corrective action, obtaining agreement from

the relevant people if required, to delivery the critical budget

outcomes

P10 propose revisions to the budget plan, if necessary, in

response to variances and/or significant or unforeseen

developments, and discuss and agree the revisions with the

relevant people in the organisation

P11 provide ongoing information on performance against

the budget plan to relevant people in your organisation

P12 gather information from implementation of the budget

plan to assist in the preparation of future project plans

P13 present the results of the work done to the appropriate

people, in accordance with departmental and organisational

procedures

Knowledge and understanding

You need to know and understand:

K1 the health and safety requirements of the area in which

you are carrying out the scientific or technical activities

K2 the implications of not taking account of legislation,

regulations, standards and guidelines when conducting

scientific or technical activities

K3 the scientific or technical techniques and processes you

must use correctly in the workplace.

K4 the importance of wearing protective clothing, gloves

and eye protection for scientific or technical activities

K5 the importance of correct identification, and any unique

workplace coding system

K6 the organisational requirements for maintaining the

security of the workplace and keeping confidential

documents

K7 the workplace business aims and goals and the

planning process

K8 the workplace organisational structure, its values and

culture

K9 how your scientific or technical activities add value

through delivering workplace products, services and

processes

K10 the lines of communication and responsibilities in your

department, and the links with the rest of the organisation

K11 the limits of your own authority and to whom you

should report if you have problems that you cannot resolve

K12 how to identify and assess the scientific or technical

requirements of your work role

K13 the different ways in which you are set your agreed

personal work objectives

K14 the different perspectives and approaches that are

important when exercising autonomy or judgement about

scientific or technical activities used

K15 the types of investigation initiated and used to review

the effectiveness or appropriateness of methods, action

and results of your scientific or technical work

K16 the budget responsibilities, including the limits of your

authority, for your workplace role

K17 the budget information available in your organisation

K18 the scientific or technical activities for which budgets

have been allocated

K19 the budgeting period(s) used in your workplace

K20 the workplace procedures for the preparation and

approval of budgets

K21 the workplace procedures for monitoring and reporting

of performance against existing and revised budgets

K22 the workplace systems established for managing and

evaluating performance against budgets

K23 the people in the workplace who need information on

the financial performance of your area

K24 the procedures for presenting financial information and

the timescales/deadlines for delivering this information

Scope/range

- discuss and agree budgets with one of the following

- people:

- 1.1 manager

- 1.2 head of school

- 1.3 vice principal

- 1.4 director

- 1.5 head teacher

- 1.6 principal

- agree business and scientific or technical work objectives

- that are all the following:

- 2.1 specific

- 2.2 achievable

- 2.3 time-bound

- 2.4 measureable

- 2.5 realistic

- establish and use effective methods for all of the

- following:

- 3.1 keeping staff informed of budget plans and

- developments

- 3.2 specifying what is expected of team leaders and their

- staff and their accountabilities

- 3.3 monitoring the budgets for scientific or technical work

- and progress against workplace plans and take appropriate

- corrective action, where necessary

- 3.4 details that are critical to monitoring budgets and

- achieving successful business results

- 3.5 identifying common budgeting issues and trends and

- their impact upon current and future spending

- record details of the work activities, and communicate

- the details to the appropriate people, using:

- 4.1 verbal report plus one method from the following:

- 4.2 written or typed report

- 4.3 computer-based record

- 4.4 specific workplace documentation

- 4.5 electronic mail

Developed by

Cogent

Date Approved

01 Nov 2023

Indicative Review Date

01 Nov 2027

Validity

Current

Status

Original

Original URN

COGLATA4-08

Relevant Occupations

Professional Occupations, Science, Science and Mathematics Science, Science Professionals

Suite

Laboratory and Associated Technical Activities Suite 4 2010, Scientific Technology Suite 3

Keywords

laboratory, technical, LATA, prepare, budgets, scientific, workplace, manager, verbal report, measurable, specific