| COSVR723 Supervise demolition activities |  |
| --- | --- |

Overview

"This standard is about supervising and monitoring demolition activities, pre-work and progress checks, controlling necessary resources, identifying problems and implementing corrective action and adopting safe, healthy and environmentally responsible work practices in accordance with current organisational requirements which are equal to or exceed current statutory and legislative requirements

This standard is for people working in the occupational area of construction site supervision which is defined as the supervision of multiple construction trades and disciplines and can be used by operatives, supervisors and managers"

Performance criteria

You must be able to:

"P1    carry out and record the supervision of at least two of the following

programmed demolition activities which will minimise disruption

and maintain optimum performance:

1.1    soft strip

1.2    mechanical demolition

1.3    remote mechanical demolition

1.4    explosive demolition

1.5    selective demolition

1.6    diamond drilling and sawing

P2    observe organisational requirements appropriate to the work

environment for the protection of the workforce, the general

public, visitors and the environment by the application of

information sourced from at least three of the following:

2.1    methods of work

2.2    risk assessment

2.3    safe use and storage of tools and equipment

2.4    safe use and storage of materials

2.5    traffic management

2.6    emergency plans

P3    identify and assess at least three of the following faults and

problems and recommend and implement corrective action which

conforms to safe working methods and practices:

3.1    limitations of design choices

3.2    construction errors

3.3    identification of further utilities

3.4    archaeological and heritage concerns

3.5    environmental concerns

3.6    incorrect maintenance

3.7    identification of hazardous materials

3.8    breaches of security

P4    conduct and record the following pre-work demolition checks to

meet organisational requirements and maintain safe working

methods and practices:

4.1    condition

4.2    fit for purpose

4.3    health, safety, wellbeing and welfare

P5    keep accurate records of work progress checks, faults, problems,

corrective actions and quantities involved

P6    identify and assess at least three of the following resources for at

least two of the following demolition activities:

*        Resources

*

6.1    people

6.2    plant, equipment or machinery

6.3    materials and components

6.4    sub-contractors

6.5    information

6.6    work area and facilities

6.7    waste management

6.8    utility providers

*        Demolition activities

*

6.9    soft strip

6.10  mechanical demolition

6.11  remote mechanical demolition

6.12  explosive demolition

6.13  selective demolition

6.14  diamond drilling and sawing"

Knowledge and understanding

You need to know and understand:

"Performance Criteria 1

Carry out demolition

K1     how to supervise the following programmed demolition activities:

K1.1    soft strip

K1.2    mechanical demolition

K1.3    remote mechanical demolition

K1.4    explosive demolition

K1.5    selective demolition

K1.6    diamond drilling and sawing

K2    how to minimise disruption to the following during programmed

demolition activities:

K2.1    the workforce

K2.2    other personnel on site

K2.3    members of the public

K2.4    occupiers

K2.5    site visitors

K2.6    people affected by on-site operations

K2.7    other works

K3    how to apply methods that will optimise performance during

programmed demolition activities

Performance Criteria 2

Observe organisational requirements

K4    what organisational requirements apply directly to demolition

activities for the protection of the workforce, the general

public, visitors and the environment

K5    how to use organisational requirements appropriate to the work

environment for the protection of the workforce, the general public,

visitors and the environment by applying the following

information sources:

K5.1    methods of work

K5.2    risk assessment

K5.3    safe use and storage of tools

K5.4    safe use and storage of materials

K5.5    traffic management

K5.6    emergency plans

K5.7    fire safety

K5.8    hot works

K5.9    environmental factors

K5.10  temporary works

Performance Criteria 3

Identify and assess faults and problems

K6    common demolition faults and problems

K7    how to assess the following faults and problems:

K7.1    limitations of design choices

K7.2    construction errors

K7.3    identification of further utilities

K7.4    archaeological and heritage concerns

K7.5    environmental concerns

K7.6    incorrect maintenance

K7.7    identification of hazardous materials

K7.8    breaches of security

K7.9    temporary works

K8    how to make recommendations and implement the following

corrective actions to rectify the faults and problems:

K8.1    redesign

K8.2    reconfigure

K8.3    restrict

K8.4    reposition

K8.5    repair

K8.6    replace

K8.7    clean

Performance Criteria 4

Conduct pre-work checks

K9      how to conduct the following pre-work demolition checks to meet

statutory requirements of testing, examination, inspection and

certification to maintain safe working methods and practices:

K9.1    condition

K9.2    fit for purpose

K9.3    health, safety, wellbeing and welfare

K10    how to record pre-work demolition checks

K11    why you need to conduct pre-work demolition checks

Performance Criteria 5

Keep accurate records

K12    how to keep accurate records of work progress  demolition

checks including faults, problems, corrective actions and

quantities  involved

K13    why accurate records of work progress checks, faults, problems,

corrective actions and quantities involved are needed

Performance Criteria 6

Identify, assess and maintain resources

K14    how to identify and assess the following resources for the

following demolition activities:

Resources

K14.1 people

K14.2 plant, equipment and machinery

K14.3 materials and components

K14.4 sub-contractors

K14.5 information

K14.6 work area and facilities

K14.7 waste management

K14.8 utility providers

Demolition activities

K14.9 soft strip

K14.10 mechanical demolition

K14.11 remote mechanical demolition

K14.12 explosive demolition

K14.13 selective demolition

K14.14 diamond drilling and sawing

K14.15 temporary works

K15    how to assess the quality of resources for demolition activities

and drilling and sawing activities

K16    how to maintain the resources for demolition activities and drilling

and sawing activities"

Developed by

CITB

Version Number

2

Date Approved

30 Sept 2020

Indicative Review Date

30 Sept 2025

Validity

Current

Status

Original

Originating Organisation

CITB

Original URN

VR723

Relevant Occupations

Construction and Building Trades Supervisors

Suite

Construction Site Supervision

Keywords

Supervise; Monitoring; Controlling; Demolition; Strip; Mechanical; Explosive; Selective