| COSVR698 Supervise the pre-installation planning for retrofit works |  |
| --- | --- |

Overview

This standard is about supervising the pre-installation planning for retrofit works by supervising the workforce to conduct pre installation checks, reviewing information sources, implementing the project programming and planning of works to include a selection of resources in accordance with organisational requirements which are equal to or exceed current statutory and legislative requirements

This standard is for people working in the occupational area of construction site supervision which is defined as the supervision of multiple construction trades and disciplines and can be used by operatives, supervisors and managers

Performance criteria

You must be able to:

P1      supervise the workforce to conduct pre-installation checks in

accordance with organisational requirements for at least six of the

following:

1.1      accuracy and completeness of project information

1.2      building condition

1.3      health and safety hazards

1.4      fire safety

1.5      temporary works

1.6      protection of existing fabric and services

1.7      suitability of materials

1.8      working in and around buildings and their occupants and

neighbouring properties

1.9      environment and ecology including but not limited to

safeguarding protected species

1.10    heritage significance

1.11    discovery architectural and archaeological features

P2      supervise the workforce to conduct external and internal

pre-installation building inspections, and report findings to the

person responsible for at least eight of the following:

2.1      suitable access

2.2      property suitability

2.3      adjoining structures

2.4      structural integrity

2.5      hazardous materials

2.6      dampness

2.7      decay

2.8      exposure ratings

2.9      combustion appliances, flues and ventilation

2.10    services (gas, electric, water, media cables)

P3      supervise control measures against identified risks arising from

external and internal pre-installation building inspections for at

least eight of the following:

3.1      suitable access

3.2      property suitability

3.3      adjoining structures

3.4      structural integrity

3.5      hazardous materials

3.6      dampness

3.7      decay

3.8      exposure ratings

3.9      combustion appliances, flues and ventilation

3.10    services (gas, electric, water, media cables)

P4      supervise control measures against identified technical and

procedural risks for at least eight of the following:

4.1      accuracy and completeness of project information

4.2      building condition

4.3      health and safety hazards

4.4      fire safety

4.5      temporary works

4.6      protection of existing fabric and services

4.7      suitability of materials

4.8      working in and around buildings and their occupants

and neighbouring properties

4.9      environment and ecology including but not limited to

safeguarding protected species

4.10    heritage significance

4.11    discovery of architectural or archaeological features

P5      interpret and utilise information sources against on-site

conditions to contribute to the retrofit works plan, risk

assessments and method statements for at least four of

the following:

5.1      drawings, design and specification information

5.2      building performance criteria to industry standards

5.3      manufacturers' technical information and product data

sheets

5.4      sub-contractor methods and scope of works

5.5      surveys

5.6      tests

5.7      examinations

5.8      specialist reports

5.9      statutory consents

5.10    current legislation, official and technical guidance

5.11    written scheme of investigation (WSI) for archaeology

P6      report issues with the planned retrofit works and suggest

corrective actions for at least six of the following information

sources:

6.1      risk assessments

6.2      method statements

6.3      drawings, design and specification information

6.4      building performance criteria to industry standards

6.5      manufacturers' technical information and product data

sheets

6.6      sub-contractor methods and scope of works

6.7      surveys

6.8      tests

6.9      examinations

6.10    specialist reports

6.11    statutory consents

6.12    current legislation, official and technical guidance

6.13    the limitations, defects of the materials and their

characteristics

6.14    written scheme of investigation (WSI) for archaeology

P7      assess the project programme and contribute to the planning and

sequencing of works for the installation of retrofit works for at

least five of the following:

7.1      repair

7.2      stabilisation

7.3      temporary works

7.4      opening-up and investigations

7.5      removal of fabric, structure or services, and making good

7.6      preparing the building for installation of fabric measures

7.7      installation of fabric, structure or services

7.8      testing

7.9      commissioning

7.10    handover

P8      contribute to the planning for the efficient use of the

resources required for retrofit works, for at least four of the

following:

8.1      materials and components

8.2      services

8.3      plant, equipment or machinery

8.4      workforce

8.5      information

8.6      site facilities

8.7      waste management

8.8      structures

8.9      storage of materials within specified parameters

Knowledge and understanding

You need to know and understand:

Performance Criteria 1

Supervise pre-installation checks

K1      why pre-installation checks, in accordance with organisational

requirements, are necessary and how to supervise them

K2      why accuracy and completeness of project information is

required, and how to determine these

K3      the implications of building conditions and common building

defects for retrofit works including but not limited to:

K3.1      moisture ingress including but not limited to: damp,

salts and causes of dampness, rain penetration, rising

damp

K3.2      internal moisture vapour

K3.3      poor indoor air quality

K3.4      inadequate ventilation

K3.5      existing and damaged services

K3.6      structural defects

K4      the importance of building condition and repair and

maintenance as the first stage in energy efficiency improvements

K5      specific health and safety hazards including but not limited to

failure of fire safety systems, poor ventilation for the

workforce (roof space, inside the property and under floor) and

services

K6      how to supervise temporary works as required during

retrofit works

K7      why protection of existing fabric and services is required and

how to do this

K8      the difference in performance characteristics between traditional

and modern materials and construction methods with particular

reference to the breathability and permeability characteristics of

traditional building fabric

K9      why identifying building materials and construction methods

for buildings of different ages including alterations and additions

is required and how to do this

K10    the materials proposed are suitable and in sufficient quantity

to achieve the design outcomes

K11    how to work in and around buildings and their occupants

including neighbouring properties and site constraints

K12    the potential environmental and ecological impacts of retrofit

works and how to respond including but not limited to

safeguarding protected species

K13    key terms and concepts including heritage values, heritage

significance, heritage impact assessment, sustainable

development and management of traditional and historic

buildings and structures

K14    legislation and official guidance specific to heritage, traditional

and protected buildings

K15    why reporting the discovery of architectural or archaeological

features to the person responsible is required and how to do

this

Performance Criteria 2

Supervise pre-installation building inspections

K16    why the supervision of the workforce to conduct external and

internal pre-installation building inspections, and report

findings to the person responsible is required

K17    how to supervise the workforce to conduct external and

internal pre-installation building inspections and report to the

person responsible for the following:

K17.1    suitable access

K17.2    property suitability

K17.3    adjoining structures

K17.4    structural integrity

K17.5    hazardous materials

K17.6    dampness

K17.7    decay

K17.8    exposure ratings

K17.9    combustion appliances, flues and ventilation

K17.10  services (gas, electric, water, media cables)

K17.11  invasive species

K18    how to identify and respond to hazards including hazardous

materials, fire safety, and flues and ventilation (incorrectly

installed, blocked, damaged and insufficient)

Performance Criteria 3

Supervise control measures against identified risks from pre-installation building inspections

K19    why supervision of control measures against identified risks

arising from external and internal pre-installation building

inspections is required

K20    how to supervise control measures against identified risks

arising from external and internal pre-installation building

inspections for the following:

K20.1    suitable access

K20.2    property suitability

K20.3    adjoining structures

K20.4    structural integrity

K20.5    hazardous materials

K20.6    dampness

K20.7    decay

K20.8    exposure ratings

K20.9    combustion appliances, flues and ventilation

K20.10  services (gas, electric, water, media cables)

K20.11  invasive species

K21    how to recognise, record and report the key issues from external

and internal pre-installation building inspections that may

affect the commencement of the work whilst working within

your authority to rectify or suspend works

Performance Criteria 4

Supervise control measures against risks

K22    why the supervision of control measures against identified

technical and procedural risks are required

K23    how to supervise control measures against identified

technical and procedural risks for the following:

K23.1    accuracy and completeness of project information

K23.2    building condition

K23.3    health and safety hazards

K23.4    fire safety

K23.5    temporary works

K23.6    protection of existing fabric and services

K23.7    suitability of materials

K23.8    working in and around buildings and their

occupants and neighbouring properties

K23.9    environment and ecology including but not limited

to safeguarding protected species

K23.10  heritage significance

K23.11  discovery of architectural and archaeological

features

K24    how to apply the principles of fire safety legislation and guidance

relating to the retrofit installation and use of the building

K25    how to supervise the work onsite using any statutory or

manufacturers requirements for testing and maintaining fire

prevention and protection systems and records

K26    how to recognise, record and report the key issues from technical

and procedural risks that may affect the commencement of

the work whilst working within your authority to rectify or suspend

works

Performance Criteria 5

Interpret and utilise information sources

K27    why the interpretation and utilisation of information sources

against on-site conditions to contribute to the retrofit works plan,

risk assessments and method statements are required for the

following:

K27.1    drawings, design and specification information

K27.2    building performance criteria to industry standards

K27.3    manufacturers' technical information and product data

sheets

K27.4    sub-contractor methods and scope of works

K27.5    surveys

K27.6    tests

K27.7    examinations

K27.8    specialist reports

K27.9    statutory consents

K27.10  current legislation, official and technical guidance

K27.11  written scheme of investigation (WSI) for archaeology

K28    how to interpret and utilise information sources against on-site

conditions to contribute to the retrofit works plan, risk

assessments and method statements for the following:

K28.1    drawings, design and specification information

K28.2    building performance criteria to industry standards

K28.3    manufacturers' technical information and product data

sheets

K28.4    sub-contractor methods and scope of works

K28.5    surveys

K28.6    tests

K28.7    examinations

K28.8    specialist reports

K28.9    statutory consents

K28.10  current legislation, official and technical guidance

K28.11  written scheme of investigation (WSI) for archaeology

K29    why compliance with relevant legal duties and fire safety

standards during the construction phase of retrofit works is

required and how to do this

K30    why documented information for fire safety including advising and

sharing information with the person responsible is required

Performance Criteria 6

Report issues and suggest corrective actions

K31    why it is important to report issues with the planned retrofit works,

and suggest corrective actions

K32    how to report issues with the retrofit works and suggest

corrective actions for the following:

K32.1    risk assessments

K32.2    method statements

K32.3    drawings, design and specification information

K32.4    building performance criteria to industry standards

K32.5    manufacturers' technical information and product data

sheets

K32.6    sub-contractor methods and scope of works

K32.7    surveys

K32.8    tests

K32.9    examinations

K32.10  specialist reports

K32.11  statutory consents

K32.12  current legislation, official and technical guidance

K32.13  the limitations, defects of the materials and their

characteristics

K32.14  written scheme of investigation (WSI) for archaeology

**

Performance Criteria 7**

Assessing the project programme, planning and sequencing of works

K33    why it is required, and how to assess the project programme for

working on and around existing buildings and structures

K34    why it is required and how to contribute to the planning and

sequencing of works for the installation of retrofit works for

the following:

K34.1    repair

K34.2    stabilisation

K34.3    temporary works

K34.4    opening-up and investigations

K34.5    removal of fabric, structure or services, and making

good

K34.6    preparing the building for installation of fabric

measures

K34.7    installation of fabric, structure or services

K34.8    testing

K34.9    commissioning

K34.10  handover

K35    how to produce method statements for working on and around

existing buildings and structures

K36    why avoiding potential thermal and hygrothermal performance

risks of failure is required, and how to do this through

planning and sequencing of works including but not limited to:

K36.1    thermal bridges

K36.2    ventilation

K36.3    thermal bypass

K36.4    condensation and interstitial condensation

K36.5    alterations in structure including materials, components

and the building

K36.6    moisture movement

K36.7    optimisation of heating systems

K37    the implications to planning and sequencing of offsite

construction methods and onsite assembly

Performance Criteria 8

Contribute to the planning for the resources required

K38    why it is required, and how to plan the efficient use of resources

for retrofit works:

K38.1    materials and components

K38.2    services

K38.3    plant, equipment or machinery

K38.4    workforce

K38.5    information

K38.6    site facilities

K38.7    waste management

K38.8    structures

K38.9    storage of materials within specified parameters

K39    how to recognise and determine when specialist skills and

knowledge are required and how to resource accordingly

including but not limited to:

K39.1    electrical

K39.2    gas

K39.3    asbestos

K39.4    radon

K39.5    heritage

K39.6    ecology

K39.7    ventilation

K39.8    fire safety

Developed by

Construction Skills

Version Number

1

Date Approved

30 Sept 2020

Indicative Review Date

30 Sept 2025

Validity

Current

Status

Original

Originating Organisation

CITB

Original URN

VR698

Relevant Occupations

Building Trades, Construction Supervisor

Suite

Construction Site Supervision

Keywords

Retrofit; retrofit works; retrofit measures; pre-installation; planning;